## Sheet1
NAME | Aigars Putnins |  |  | PROJECT | Banshee
REF/# | RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | MITIGATION | RISK RATING KEY
1 | Flight Controller Software Failure | UNDESIRABLE | IMPROBABLE | MEDIUM | Software failure will be mitigated by using the Arduino Pro Mini to process the inputs. |  | SEVERITY
2 | Hardware Failure | UNDESIRABLE | IMPROBABLE | MEDIUM | Hardware failure will be mitigated by covering any vital spots that could be damaged like the flight controller. | LIKELIHOOD |  | ACCEPTABLE | TOLERABLE | UNDESIRABLE | INTOLERABLE
3 | Controller Failure | IMPROBABLE | TOLERABLE | MEDIUM | If the controller fails the failsafe on the quad-copter will slowly descend the drone, minimising damage. |  | IMPROBABLE | LOW | MEDIUM | MEDIUM | HIGH
4 | Fire Hazard | IMPROBABLE | INTOLERABLE | HIGH | The risk of fire will be mitigated by using the power distribution board that evenly provides power to flight controller and the motors. |  | POSSIBLE | LOW | MEDIUM | HIGH | EXTREME
5 | Water Hazard | IMPROBABLE | UNDESIRABLE | MEDIUM | The client has to understand that the drone should not be flown over open water. It is outlined that the drone is not water proof. If the amount of water is low the drone should be turned off immediately and the wet part should be dried. |  | PROBABLE | MEDIUM | HIGH | HIGH | EXTREME
|  |  |  | SUMMARY | In summary, the project Banshee is highly vulnerable to fire, however this risk is unlikely to occur as the system will automatically shut-down when the components overheat. The client has to understand that the quad-copter should be turned off when not in use to avoid any fire hazard. The water hazard can't be avoided if the system is submerged as it will damage all components. The client has to understand that the device is not water proof and it can't be flown in rain.